## TestCase
Product Name |  | ShopCart | TC Start Date | 2024-04-09 | TC Execution Start Date | 2024-06-09 |  |  |  |  | TEST CASE
Module Name |  | Registration | TC End Date | 2024-05-09 | TC Execution End Date | [5 empty] | PASS | 12
Epic |  |  | Test Case Developed By |  | Browser (tested) | Yes |  |  |  |  | FAIL | 5
Developer Name (TL) |  |  | Test Case Reviewed By |  | Performance (tested) | Yes |  |  |  |  | Not Executed | 0
Test Executed by | [10 empty] | Out of Scope | 0
[11 empty] | TOTAL | 17
#SL | Module | Type of Testing | Features | Test Cases | Exepected Result | Actual Result | Test Data | Reproducing Steps | Bug Screen Shot | Dev Comments | Final Status | Remarks
1 |  | Browser Compatibility Testing |  | Checking by running the site in different browsers | Should run in different browsers | Found as per expectation | Chrome, Mozilla Firefox, Microsoft Edge, Opera Mini | 1. Go to different browsers 2. Search 'ShopCart' 3. Goto the website |  |  | Passed
2 | Registration | UI Testing | Registration | Checking spelling or grammatical mistakes | No spelling or grammatical mistakes | Found as per expectation | N/A | 1. Goto the URL https://shopcart.com.bd/ 2. Click on Registration button at the right corner 3. Check the spelling and grammar of the website |  |  | Passed
3 |  |  |  | Verifying the font, text color and style | Should be as per the requirement | Found as per expectation | N/A | 1. Goto the URL https://shopcart.com.bd/ 2. Click on Registration button at the right corner 3. Check the font, text color and style |  |  | Passed
4 |  |  |  | Checking mandatory field is marked with a red asterisk | Red asterisk must be present | Not found as per expectation | N/A | 1. Goto the URL https://shopcart.com.bd/ 2. Check red asterisk beside mandatory field | URL |  | Failed
5 |  |  |  | Checking by hovering over the fields | A text should appear over the fields | Found as per expectation | N/A | 1. Goto the URL https://shopcart.com.bd/ 2. Hover over every fields |  |  | Passed
6 |  |  |  | Checking Phone Number fields error message size | Error message should be red colour and bold | Not found as per expectation | N/A | 1. Goto the URL https://shopcart.com.bd/ 2. Click on Registration button at the right corner 3.Keep all mandatory field blank | URL |  | Failed
7 |  |  |  | Checking alignment of the fields | All the fields should be in left alignment | Found as per expectation | N/A | 1. Goto the URL https://shopcart.com.bd/ 2. Click on Registration button at the right corner 3. Check alignment of the fields | URL |  | Passed
8
9
44 |  | Functional Testing |  | Leave the required field blank | Sholud not allow user to register and pop an message for fillup the field | Found as per expectation | N/A | 1. Goto the URL https://shopcart.com.bd/ 2. Click on Registration button at the right corner 3.Keep one mandatory field blank | URL |  | Passed
45 |  |  |  | Verifying Full Name field is case insensitive | Should accept the provided input | Found as per expectation | MMnn | 1. Goto the URL https://shopcart.com.bd/ 2. Input MMnn in Full Name field |  |  | Passed
46 |  |  |  | Give a blank space at first position in Full Name field | Should not accept the provided input | Not found as per expectation | Mou | 1. Goto the URL https://shopcart.com.bd/ 2. Click on Registration button at the right corner 3. Input space at first position of Full Name field | URL |  | Failed
47 |  |  |  | Verifying alert message for all required fields | Should give an error message | Found as per expectation | N/A | 1. Goto the URL https://shopcart.com.bd/ 2. Click on Registration button at the right corner 3. Keep blank all the field and check | URL |  | Passed
|  |  |  | Giving some special characters in the Full Name field | Should not accept the provided input | Not found as per expectation |  | 1. Goto the URL https://shopcart.com.bd/ 2. Click on Registration button at the right corner 3. Enter special characters in Full Name field | URL |  | Failed
|  |  |  | Inputing Full Name with alphabets | Should accept the provided input | Found as per expectation | Munia Mishu | 1. Goto the URL https://shopcart.com.bd/ 2. Click on Registration button at the right corner 3. Enter alphabets in Full Name field | URL |  | Passed
|  |  |  | Giving comma between alphabets for Full Name | Should not accept the provided input | Not found as per expectation | mm,nn | 1. Goto the URL https://shopcart.com.bd/ 2. Click on Registration button at the right corner 3. Enter comma between alphabets in Full Name field | URL |  | Failed
|  |  |  | Giving same Email Address for create another account | Should not allow the provided input | Found as per expectation | muniamishu600@gmail.com | 1. Goto the URL https://shopcart.com.bd/ 2. Click on Registration button at the right corner 3. Enter a email address which is already used | URL |  | Passed
|  |  |  | Giving same Phone Number for create another account | Should not allow the provided input | Found as per expectation | 1407786860 | 1. Goto the URL https://shopcart.com.bd/ 2. Click on Registration button at the right corner 3. Enter a phone number which is already used | URL |  | Passed
|  |  |  | Check email verification | should give a verification code by email | Found as per expectation |  | 1. Goto the URL https://shopcart.com.bd/ 2. Click on Registration button at the right corner 3. Fulfill all the fields and click create account button 4. Enter into the given email address |  |  | Passed
48 |  | Usability Testing
49
50
51 |  | Functionality Testing | Sign In
52
53
54
55
56
57
58
59
60
61
62
Improvement Scopes
Negative test

## Report
Test Case Report
Project Name | ShopCart
Module Name | Registration |  |  |  |  | Total No. | Status | Result :
Test Case Version | [5 empty] | 12 | PASS
Written By | [5 empty] | 5 | FAIL
Executed By | [5 empty] | 0 | Not Executed | New Features | Testing Scope | Testing Environment : | Google Chrome Browser
Reviewed By | [5 empty] | 0 | Out of Scope
TEST EXECUTION REPORT
Test Case | PASS | FAIL | Not Executed | Out Of Scope | Total TC
| 12 | 5 | 0 | 0 | 17
Grand Total | 12 | 5 | 0 | 0 | 17
LIMITATIONS
Documents |  |  |  | Received | Useful
PRD |  |  |  | No | No
USER STORY |  |  |  | No | No
| Testing Type in Scope | Description
Yes/ No. Justification (If No): | Functional Testing | This type of testing ignores the internal parts and focuses only on the output to check if it is as per the requirement or not.
Yes/ No. Justification (If No): | Integration Testing | Testing of all integrated modules to verify the combined functionality after integration is termed as Integration Testing.
Yes/ No. Justification (If No): | Negative Testing | Testing having the mindset of “attitude to break” using incorrect data and invalid inputs.
Yes/ No. Justification (If No): | Usability Testing | Test application from user friendliness perspective.
Yes/ No. Justification (If No): | Browser Compatibility Testing | Browser Compatibility Testing is performed for web applications and it ensures that the software can run with the combination of different browser and operating system. This type of testing also validates whether web application runs on all versions of all browsers or not.
Yes/ No. Justification (If No): | Boundary Value Testing | There is an upper and lower boundary for each range and testing is performed on these boundary values.
Yes/ No. Justification (If No): | Risk Based Testing Or Regression Testing | Risk-Based Testing includes testing of highly critical functionality, which has the highest impact on business and in which the probability of failure is very high. Testing an application as a whole for the modification in any module or functionality is termed as Regression Testing.

## Bug Report
Bug Reporting
# SL 4
Issue: Mandatory field is not marked with a red asterisk
Reproducing Steps:
1. Goto the URL https://shopcart.com.bd/ 2. Check red asterisk beside mandatory field
Env: Production Credentials:usename //Password
Module: Registration
Priority: P1
Screenshot: Link
Responsible QA: Mishu